DIJIPEOPLE People operations, simplified and scalable

Maseer Group Customer Onboarding and Training Plan

Phase 1 rollout of Employee, Leave, Attendance, Settings and Dashboard modules

| Prepared for | Maseer Group / Maseer Tech (final customer name to be confirmed) |
| --- | --- |
| Prepared by | Taimur Israr / DijiPeople |
| Document status | Planning baseline |
| Version | 1.0 |
| Date | 5 August 2026 |

Purpose: Provide a practical, budget-conscious plan that can be executed without over-engineering the first customer rollout.

# Document map

This document is structured for decision-making first, followed by implementation detail.

| 1 | Purpose, partnership context and rollout recommendation |
| --- | --- |

| 2 | Phase 1 scope and feasibility assessment |
| --- | --- |

| 3 | Implementation approach, governance and responsibilities |
| --- | --- |

| 4 | Data preparation and configuration requirements |
| --- | --- |

| 5 | Four-week onboarding and go-live timeline |
| --- | --- |

| 6 | Role-based training programme and session plan |
| --- | --- |

| 7 | UAT, cutover, support and acceptance criteria |
| --- | --- |

| 8 | Phase 2 roadmap and decisions required |
| --- | --- |

# 1. Purpose and rollout recommendation

| 5 Phase 1 modules | 4 weeks implementation and readiness | 7 Sep 2026 target go-live | 2 weeks hypercare |
| --- | --- | --- | --- |

This plan covers the first DijiPeople customer rollout for Maseer Group or Maseer Tech. The final legal/customer name is intentionally left as a confirmation item. The commercial relationship is understood as a partnership in which Sir Saud owns Maseer Group and Taimur Israr owns DijiPeople. DijiPeople currently operates in association with Maseer Group but is expected to become a separate product/business over time.

Recommendation Run a controlled Phase 1 rather than exposing every available module. Start with employee records, leave, attendance, tenant settings and dashboards; stabilise real usage; then release recruitment and onboarding as Phase 2.

## Target outcome

Maseer has a configured tenant with accurate employee and organisation data.

Employees can access their profile, submit leave and use the agreed attendance method.

Managers can review attendance and approve or reject leave requests.

HR administrators can maintain employees, leave policies, attendance settings, holidays and user access.

Leadership can view trusted Phase 1 dashboard metrics.

DijiPeople has documented support, issue triage and change-control processes for its first production customer.

# 2. Phase 1 scope and feasibility

## In scope

| Module | Phase 1 capabilities | Primary users |
| --- | --- | --- |
| Employee | Employee master records, organisation placement, reporting manager, status, contact and employment information. | HR administrators, managers, employees. |
| Leave | Leave types, policies, entitlement/balances, request, approval, rejection, cancellation and dashboard reporting. | Employees, managers/approvers, HR. |
| Attendance | Work schedules, weekends/holidays, attendance capture, late/early handling, exceptions and attendance views. | Employees, managers, HR, IT for desktop deployment. |
| Settings | Tenant branding, organisation structure, locations, departments, teams, roles, permissions and operational settings required by Phase 1. | DijiPeople administrator and Maseer HR/IT administrators. |
| Dashboard | Headcount, leave, attendance and operational summary cards using approved Phase 1 data. | Leadership, HR and managers subject to role access. |

## Deferred to later phases

Recruitment, candidate pipeline and job management.

Employee onboarding workflows, joining documents and induction tasks.

Payroll, compensation, loans, benefits and statutory processing.

Performance management, learning, contracts, projects and advanced analytics.

Any integration that is not required for Phase 1 attendance, identity or notifications.

## Feasibility assessment

| Area | Assessment | Condition |
| --- | --- | --- |
| Functional readiness | Feasible | Employee, leave, attendance, settings and dashboard flows must pass staging regression and tenant-isolation tests. |
| User volume | Feasible | Approximately 100 users is within the proposed starter infrastructure; attendance peak testing is required. |
| Data migration | Feasible with templates | Maseer must provide complete, validated employee, hierarchy, leave-balance and schedule data by 14 August 2026. |
| Desktop attendance | Feasible with controlled pilot | The Electron installer must be signed or the unsigned-installation risk formally accepted. Test on representative Windows devices. |
| Timeline | Feasible in four weeks | Requires one accountable Maseer HR lead, timely decisions and no major scope expansion. |
| Go-live | Target 7 September 2026 | Subject to UAT, production-readiness and training gates. |

Critical dependency The production platform must be ready before customer cutover. If deployment, credentials, database backups or desktop packaging are not production-safe, move the go-live date rather than accepting avoidable risk.

# 3. Implementation approach and governance

## Guiding principles

Configure the standard product first. Avoid customer-specific code unless a confirmed business requirement cannot be met through tenant settings or reusable rules.

Use a train-the-trainer model: DijiPeople trains Maseer HR/admin champions, who then help reinforce employee adoption.

Use real Maseer processes and approved data in UAT, not generic demonstrations.

Maintain one controlled issue list with severity, owner, target date and release decision.

Freeze Phase 1 scope after the kickoff. New ideas go into the Phase 2 backlog unless they block legal, security or operational use.

## Roles and responsibilities

| Role | Named owner / placeholder | Responsibilities |
| --- | --- | --- |
| Executive sponsor | Sir Saud | Confirms business priority, resolves organisational blockers and approves go-live. |
| DijiPeople product owner and implementation lead | Taimur Israr | Owns product readiness, solution decisions, configuration, training, deployment coordination and final release recommendation. |
| Maseer project coordinator / HR lead | To be nominated | Supplies data and policies, coordinates users, validates configuration, manages UAT and confirms acceptance. |
| Maseer HR administrators | To be nominated | Attend detailed training, verify employee/leave/attendance setup and provide first-line process support. |
| Maseer IT representative | To be nominated | Supports user accounts, Windows desktop deployment, network access and local device troubleshooting. |
| Managers / approvers | Department representatives | Validate approval routing, attendance visibility and manager dashboards. |
| Pilot employees | 5–10 representative users | Test self-service, attendance and leave journeys before broad go-live. |

## Governance cadence

| Meeting | Cadence | Participants | Purpose |
| --- | --- | --- | --- |
| Project checkpoint | Twice weekly during onboarding | Taimur, Maseer HR lead, IT as needed | Review progress, decisions, risks and blockers. |
| UAT triage | Daily during UAT week | Taimur and testers | Classify issues, confirm fixes and protect go-live scope. |
| Go-live checkpoint | Daily during first week | Sponsor or delegate, HR lead, Taimur | Review adoption, incidents and business continuity. |
| Stabilisation review | End of hypercare | Sponsor, HR, Taimur | Accept Phase 1 and agree Phase 2 priorities. |

# 4. Data and configuration requirements

Data cut-off Maseer should provide the first complete data pack by Friday, 14 August 2026. Late or incomplete data is the most likely cause of a delayed go-live.

## Required data pack

| Data set | Minimum contents | Owner | Validation |
| --- | --- | --- | --- |
| Organisation structure | Legal entity, business units, departments, teams, locations, designations and employee levels. | Maseer HR | Names are unique; inactive structures are identified. |
| Employee master | Employee code, name, work email, mobile, hire date, status, location, department/team, designation, level, manager and employment type. | Maseer HR | Unique employee code/email; every active employee has a valid manager or approved exception. |
| Users and roles | Users requiring login, HR admins, managers, approvers and leadership dashboard viewers. | Maseer HR + IT | Least-privilege role assignment approved. |
| Leave configuration | Leave types, entitlement, accrual, carry-forward, probation rules, attachments, approval route and balance as of cutover. | Maseer HR | Balance total reconciles to existing HR record. |
| Attendance configuration | Workweek, weekends, holidays, shifts, grace periods, late/early rules, overtime treatment and permitted check-in modes. | Maseer HR + IT | Rules signed off and pilot devices identified. |
| Branding and communications | Customer display name, logo, support contact and employee announcement approver. | Sponsor / HR | Final customer name confirmed before production invitations. |
| Dashboard definitions | Approved KPI definitions and visibility by role. | Sponsor + HR | Counts reconcile to imported source data. |

## Data migration method

1.  DijiPeople issues controlled Excel/CSV templates with required fields, examples and allowed values.

2.  Maseer completes the files and performs an internal first review before submission.

3.  DijiPeople validates duplicates, missing relationships, invalid dates, unsupported values and leave-balance totals.

4.  A first import is performed in staging and a reconciliation report is returned.

5.  Maseer corrects the source file rather than making uncontrolled staging edits where possible.

6.  The approved final file is frozen for production cutover and retained as migration evidence.

7.  Post-import checks confirm employee count, active/inactive count, manager relationships, balances, shifts and role access.

## Configuration decision log

| Decision | Required by | Default recommendation |
| --- | --- | --- |
| Final customer display/legal name | 14 Aug 2026 | Use “Maseer Group” as the working name until confirmed. |
| Attendance capture mode | 14 Aug 2026 | Desktop agent for office devices plus authorised administrative correction; avoid multiple uncontrolled methods at launch. |
| Leave approval model | 17 Aug 2026 | Reporting manager first, then HR only where policy requires. |
| Weekend and holiday calendars | 17 Aug 2026 | One primary calendar initially; add location-specific calendars only when genuinely required. |
| Employee invitation method | 28 Aug 2026 | Staged invitations to pilot users, then remaining users after final readiness approval. |
| Support channel | 28 Aug 2026 | One designated email or collaboration channel with an issue template. |

# 5. Onboarding timeline

| Period | Workstream | Activities and deliverables |
| --- | --- | --- |
| Week 1 — 10–14 Aug | Kickoff and discovery | Kickoff with Sir Saud and nominated HR lead; confirm customer name, employee count, attendance approach and approval model; issue data templates; confirm pilot group; approve Phase 1 scope and timeline. |
| Week 2 — 17–21 Aug | Configuration and first migration | Configure tenant, branding, structure, roles, leave policies, holidays, schedules and dashboards in staging; import first data pack; deploy desktop agent to pilot devices; reconcile migration results. |
| Week 3 — 24–28 Aug | UAT and administrator training | Execute employee, leave, attendance, settings and dashboard UAT; fix critical/high defects; train DijiPeople/Maseer administrators and HR operations; freeze production configuration baseline. |
| Week 4 — 31 Aug–4 Sep | Final training and cutover readiness | Complete final data delta; run manager and employee training; complete production smoke tests; issue user guide; obtain UAT and go-live approvals; schedule user invitations and desktop rollout. |
| Go-live — 7 Sep | Controlled production release | Enable production access; deploy attendance agent; validate first check-ins, leave request/approval and dashboard counts; open support channel and daily checkpoint. |
| Hypercare — 7–18 Sep | Stabilisation | Daily issue review, adoption tracking, configuration corrections, minor fixes and knowledge transfer to Maseer HR/IT champions. |
| Review — 21–25 Sep | Phase 1 closure and Phase 2 planning | Confirm acceptance, measure adoption, review lessons learned and prioritise recruitment/onboarding rollout. |

## Key milestones

| Milestone | Target date | Approval / evidence |
| --- | --- | --- |
| Kickoff complete | 10 Aug 2026 | Scope, owners and decision log opened. |
| Complete first data pack | 14 Aug 2026 | HR lead confirms source completeness. |
| Staging configuration ready | 21 Aug 2026 | Configuration checklist and first reconciliation. |
| UAT cycle complete | 28 Aug 2026 | No open critical defects; high defects have agreed treatment. |
| Go-live readiness review | 4 Sep 2026 | Sponsor, HR lead and DijiPeople sign-off. |
| Production go-live | 7 Sep 2026 | First live attendance and leave transactions. |
| Hypercare exit | 18 Sep 2026 | Stable operations and open items transferred to backlog/support. |

# 6. Training programme

Training model Use live demonstrations in staging, role-based exercises and a short recorded recap. Do not put all users into one long generic session.

| Session | Audience | Duration | Suggested date | Coverage and exercise |
| --- | --- | --- | --- | --- |
| 1. Sponsor and leadership briefing | Sir Saud, leadership, HR lead | 45 min | 10 Aug | Objectives, scope, dashboard outcomes, responsibilities, decisions and go-live risks. |
| 2. Platform and HR administration | Maseer HR admins, IT, Taimur | 2 hours | 24 Aug | Tenant settings, structure, roles, users, employee data, leave policy and attendance configuration. Exercise: create/update a test employee and validate access. |
| 3. HR operations deep dive | HR operations team | 2 hours | 25 Aug | Employee lifecycle, leave corrections, attendance exceptions, balance adjustment, reporting and audit trail. Exercise: resolve a sample exception end to end. |
| 4. Managers and approvers | Line managers and department heads | 75 min | 31 Aug | Team view, leave approval/rejection, attendance review, escalation and dashboard interpretation. Exercise: process a leave request. |
| 5. Employee self-service | All employees, delivered in batches | 45 min | 1–2 Sep | Login, profile, leave request, balance, attendance, notifications and support. Exercise: submit and cancel a test leave request. |
| 6. IT and desktop support | Maseer IT / local support | 60 min | 3 Sep | Installer deployment, update behaviour, device permissions, connectivity, troubleshooting and escalation. |
| 7. Go-live clinic | HR, managers and pilot users | 60 min | 7 Sep | Live Q&A, first transactions and issue capture. |

## Training deliverables

Role-based quick-reference guide for employee, manager and HR administrator journeys.

Recorded or reusable demonstration covering the standard Phase 1 process.

Attendance desktop installation guide and troubleshooting checklist.

UAT scripts reused as hands-on training exercises.

Frequently asked questions and a support-escalation guide.

Training attendance and completion record for go-live evidence.

## Training success measures

| Audience | Minimum success condition |
| --- | --- |
| HR administrators | Can configure permitted settings, maintain an employee, correct an attendance exception and reconcile leave balances without DijiPeople intervention. |
| Managers | Can find their team, review attendance and complete a leave approval/rejection correctly. |
| Employees | Can sign in, view balance, submit leave and complete the agreed attendance action. |
| IT support | Can install/update the desktop agent and provide diagnostic information when escalating. |

# 7. UAT, cutover and support

## UAT coverage

| Area | Minimum test scenarios |
| --- | --- |
| Employee | Create/import employee; update structure and manager; activate/deactivate; verify employee self-view and role restrictions. |
| Leave | Submit, approve, reject, cancel, attachment rule, insufficient balance, overlapping request and manager visibility. |
| Attendance | Normal check-in/out, late arrival, missing event, weekend/holiday, shift assignment, correction and manager/HR review. |
| Settings | Branding, calendars, policy inheritance, permissions and effective-dated changes where applicable. |
| Dashboard | Headcount, leave and attendance counts reconcile to source transactions and respect role access. |
| Desktop | Fresh install, update, offline/reconnect behaviour, antivirus response and no embedded production secret. |
| Security | Cross-tenant isolation, unauthorised role access, suspended user and session expiry. |

## Defect severity and release treatment

| Severity | Definition | Go-live rule |
| --- | --- | --- |
| Critical | Outage, data loss/corruption, cross-tenant exposure, login failure for broad user groups or unusable attendance/leave process. | Must be fixed and retested before go-live. |
| High | Major process is blocked for a role or produces materially incorrect business results without a practical workaround. | Fix before go-live or obtain explicit sponsor risk acceptance with a dated fix. |
| Medium | Limited impact with a safe workaround; does not compromise data or core operation. | May enter post-go-live backlog with owner and target date. |
| Low | Cosmetic, wording or minor convenience issue. | Does not block go-live. |

## Cutover checklist

1.  Freeze approved employee, leave-balance and attendance configuration files.

2.  Create a production recovery point and verify monitoring and support contacts.

3.  Apply production configuration and import final data/delta.

4.  Run employee-count, hierarchy, leave-balance and shift reconciliations.

5.  Smoke-test administrator, manager and employee accounts.

6.  Send invitations in controlled batches, starting with HR, managers and pilot employees.

7.  Deploy the desktop agent to approved devices and confirm the first attendance event.

8.  Open the support channel, daily checkpoint and issue register.

## Hypercare support model

| Priority | Example | Target acknowledgement during business hours | Treatment |
| --- | --- | --- | --- |
| P1 | System unavailable, data exposure, broad login or attendance outage | Within 1 hour | Immediate triage; protect data and restore service first. |
| P2 | Major function unavailable for a team or incorrect leave/attendance outcome | Within 4 hours | Workaround or fix prioritised in the next safe release. |
| P3 | Single-user issue or configuration question | Within 1 business day | Resolve through support, guidance or planned correction. |
| P4 | Enhancement or cosmetic request | Within 2 business days | Add to reviewed product backlog. |

These are onboarding support targets, not a contractual SLA. A formal SLA should be agreed separately after the first-customer operating model is proven.

# 8. Acceptance and Phase 2 roadmap

## Phase 1 acceptance criteria

| Category | Acceptance condition |
| --- | --- |
| Data | All approved active employees imported; duplicates resolved; manager, organisation, leave-balance and schedule reconciliation completed. |
| Employee | Pilot and production users can securely access the correct profile and permitted functions. |
| Leave | Standard request-to-approval cycle works and balances are accurate. |
| Attendance | Agreed attendance method works on representative devices and exceptions can be corrected with an audit trail. |
| Settings | Maseer tenant, branding, structure, policies, calendars, roles and permissions are approved. |
| Dashboard | Published metrics reconcile to transactions and are visible only to authorised roles. |
| Training | Required HR, manager, employee and IT sessions delivered; guides issued; champions identified. |
| Operations | Monitoring, backups, support channel, issue triage and rollback plan are operational. |
| Defects | No open critical defects; high defects are closed or explicitly accepted. |

## Phase 2 recommendation

| Phase | Indicative timing | Scope | Entry condition |
| --- | --- | --- | --- |
| Phase 2A | Discovery after 21 Sep 2026 | Recruitment: jobs, candidates, interviews, offers and hiring pipeline. | Phase 1 stable and HR process owners available. |
| Phase 2B | Following recruitment readiness | Employee onboarding: documents, tasks, approvals, induction and conversion to employee. | Recruitment data model and handoff accepted. |
| Later roadmap | Prioritised quarterly | Timesheets, payroll, performance, contracts and additional dashboards/integrations. | Business case, product readiness and support capacity confirmed. |

## Decisions required at kickoff

| Decision | Owner | Deadline |
| --- | --- | --- |
| Confirm whether the customer name is Maseer Group, Maseer Tech or another legal/display name. | Sir Saud | 10–14 Aug 2026 |
| Nominate the Maseer HR lead and IT representative. | Sir Saud | 10 Aug 2026 |
| Confirm attendance capture mode and pilot devices. | Maseer HR + IT | 14 Aug 2026 |
| Approve leave types, policies, opening balances and approval route. | Maseer HR | 17 Aug 2026 |
| Approve pilot users and training attendee lists. | Maseer HR lead | 21 Aug 2026 |
| Approve go-live after readiness review. | Sir Saud / delegate | 4 Sep 2026 |

Bottom line The rollout is feasible for the proposed scope and user count. The schedule is deliberately tight but realistic if Maseer provides complete data and accountable decision-makers in Week 1, and DijiPeople closes the production-readiness blockers before UAT.